## Shortest Path1
Seervada Park Shortest Path Problem
Minimise the distance traveled
| From | To | On Route | Distance | Nodes | Net FIow |  | Supply/Demand
| O | A | 1 | 2 | O | 1 | = | 1
| O | B | 0 | 5 | A | 0 | = | 0
| O | C | 0 | 4 | B | 0 | = | 0
| A | B | 1 | 2 | C | 0 | = | 0
| А | D | 0 | 7 | D | 0 | = | 0
| В | C | 0 | 1 | E | 0 | = | 0
| B | D | 0 | 4 | T | -1 | = | -1
| B | Е | 1 | 3
| C | B | 0 | 1
| C | Е | 0 | 4
| D | Е | 0 | 1
| D | T | 1 | 5
| Е | D | 1 | 1
| Е | T | 0 | 7
|  | TotaI Distance | 13

## Max Flow1
Seervada Park Maximum Flow Problem
| From | To | Flow |  | Capacity | Nodes | NetFIow |  | Supply/Oemand
| O | A | 3 | <= | 5 | O | 14 | = | 14
| O | B | 7 | <= | 7 | A | 0 | = | 0
| O | C | 4 | <= | 4 | B | 0 | = | 0
| A | B | 0 | <= | 1 | C | 0 | = | 0
| A | D | 3 | <= | 3 | D | 0 | = | 0
| B | C | 0 | <= | 2 | E | 0 | = | 0
| B | D | 4 | <= | 4 | T | -14 | = | -14
| B | E | 3 | <= | 5
| C | E | 4 | <= | 4
| D | T | 8 | <= | 9
| E | D | 1 | <= | 1
| E | T | 6 | <= | 6
|  | Max Flow | 14

## Min Cost1
Distribution Unlimited Co. Minimun Cost Flow Problem
| From | To | Ship |  | Capacity | UnitCost in (100$) | Nodes | NetFIow |  | Supply/Demand
| A | B | 0 | <= | 10 | 2 | A | 50 | = | 50
| A | C | 40 |  |  | 4 | B | 40 | = | 40
| A | D | 10 |  |  | 9 | C | 0 | = | 0
| B | C | 40 |  |  | 3 | D | -30 | = | -30
| C | E | 80 | <= | 80 | 1 | E | -60 | = | -60
| D | E | 0 |  |  | 3
| E | D | 20 |  |  | 2
|  | Total Cost | 490

## PM5
The Lockhead Aircraft Co. Fighter Airplane Construction
PERT/CPM method of timecost trade-offs
|  | Time (weeks) |  | Cost (millions $)
| Activity | Normal | Crash | Normal | Crash | Max Time Reduction | Crash Cost per week |  | Start Time | Time Reduction | Finish Time
| A | 32 | 28 | 160 | 180 | 4 | 5 | A | 0 | 0 | 32
| B | 28 | 25 | 125 | 146 | 3 | 7 | B | 0 | 3 | 25
| C | 36 | 31 | 170 | 210 | 5 | 8 | C | 32 | 0 | 68
| D | 16 | 13 | 60 | 72 | 3 | 4 | D | 25 | 0 | 41
| E | 32 | 27 | 135 | 160 | 5 | 5 | E | 25 | 0 | 57
| F | 54 | 47 | 215 | 257 | 7 | 6 | F | 25 | 3 | 76
| G | 17 | 15 | 90 | 96 | 2 | 3 | G | 41 | 0 | 58
| H | 20 | 17 | 120 | 132 | 3 | 4 | H | 58 | 0 | 78
| I | 34 | 30 | 190 | 226 | 4 | 9 | I | 58 | 0 | 92
| J | 18 | 16 | 80 | 84 | 2 | 2 | J | 76 | 2 | 92
Max Time (weeks)
[8 empty] | Project Finish Time | 92 | <= | 92
[8 empty] | Total Cost | 1388

## PM4
The 21 Century Studios
PERT/CPM method of timecost trade-offs
|  | Time (weeks) |  | Cost (millions $)
| Activity | Normal | Crash | Normal | Crash | Max Time Reduction | Crash Cost per week |  | Start Time | Time Reduction | Finish Time
| A | 5 | 3 | 20 | 30 | 2 | 5 | A | 0 | 2 | 3
| B | 3 | 2 | 10 | 20 | 1 | 10 | B | 0 | 1 | 2
| C | 4 | 2 | 16 | 24 | 2 | 4 | C | 3 | 0 | 7
| D | 6 | 3 | 25 | 43 | 3 | 6 | D | 3 | 0 | 9
| E | 5 | 4 | 22 | 30 | 1 | 8 | E | 2 | 0 | 7
| F | 7 | 4 | 30 | 48 | 3 | 6 | F | 2 | 0 | 9
| G | 9 | 5 | 25 | 45 | 4 | 5 | G | 7 | 1 | 15
| H | 8 | 6 | 30 | 44 | 2 | 7 | H | 9 | 2 | 15
Max Time (weeks)
[8 empty] | Project Finish Time | 15 | <= | 15
[8 empty] | Total Cost | 217

## PM3
Good Homes Construction Company
|  | Time (weeks) |  | Cost ($)
| Activity | Normal | Crash | Normal | Crash | Max Time Reduction | Crash Cost per week |  | Start Time | Time Reduction | Finish Time
| A | 3 | 2 | 54000 | 60000 | 1 | 6000 | A | 0 | 0 | 3
| B | 4 | 3 | 62000 | 65000 | 1 | 3000 | B | 3 | 1 | 6
| C | 5 | 2 | 66000 | 70000 | 3 | 1333.3333 | C | 3 | 2 | 6
| D | 3 | 1 | 40000 | 43000 | 2 | 1500 | D | 6 | 1 | 8
| E | 4 | 2 | 75000 | 80000 | 2 | 2500 | E | 6 | 2 | 8
[11 empty] | Max Time (weeks) | Overhead cost per week
[8 empty] | Project Finish Time | 8 | <= | ? | 5000
[8 empty] | Total Cost | 349166.6667

## PM2
Tinker Construction Co. Problem
|  | Time (months) |  | Cost ($)
| Activity | Normal | Crash | Normal | Crash | Max Time Reduction | Crash Cost per month |  | Start Time | Time Reduction | Finish Time
| A | 8 | 5 | 25000 | 40000 | 3 | 5000 | A | 0 | 0 | 8
| B | 9 | 7 | 20000 | 30000 | 2 | 5000 | B | 0 | 2 | 7
| C | 6 | 4 | 16000 | 24000 | 2 | 4000 | C | 8 | 2 | 12
| D | 7 | 4 | 27000 | 45000 | 3 | 6000 | D | 7 | 2 | 12
Max Time (months)
[8 empty] | Project Finish Time | 12 | <= | 12
[8 empty] | Total Cost | 118000

## PM1
Reliable Construction Co. Project Scheduling Problem with Time-Cost Trade-ofs
PERT/CPM
|  | Normal |  | Crash
| Activity | Time | Cost | Normal | Cost | Max Time Reduction | Crash Cost per week |  | Start Time | Time Reduction | Finish Time
| A | 2 | 1 | 180000 | 280000 | 1 | 100000 | A | 0 | 0 | 2
| B | 4 | 2 | 320000 | 420000 | 2 | 50000 | B | 2 | 0 | 6
| C | 10 | 7 | 620000 | 860000 | 3 | 80000 | C | 6 | 0 | 16
| D | 6 | 4 | 260000 | 340000 | 2 | 40000 | D | 16 | 0 | 22
| E | 4 | 3 | 410000 | 570000 | 1 | 160000 | E | 16 | 0 | 20
| F | 5 | 3 | 180000 | 260000 | 2 | 40000 | F | 20 | 2 | 23
| G | 7 | 4 | 900000 | 1020000 | 3 | 40000 | G | 22 | 0 | 29
| H | 9 | 6 | 200000 | 380000 | 3 | 60000 | H | 29 | 0 | 38
| I | 7 | 5 | 210000 | 270000 | 2 | 30000 | I | 16 | 0 | 23
| J | 8 | 6 | 430000 | 490000 | 2 | 30000 | J | 23 | 2 | 29
| K | 4 | 3 | 160000 | 200000 | 1 | 40000 | K | 30 | 0 | 34
| L | 5 | 3 | 250000 | 350000 | 2 | 50000 | L | 29 | 0 | 34
| M | 2 | 1 | 100000 | 200000 | 1 | 100000 | M | 38 | 0 | 40
| N | 6 | 3 | 330000 | 510000 | 3 | 60000 | N | 34 | 0 | 40
Max Time
[8 empty] | Project Finish Time | 40 | <= | 40
[8 empty] | Total Cost | 4690000

## Shortest Path2
Route destination between cities
| From | To | On Route | Distance | Nodes | Net FIow |  | Supply/Demand
| O | A | 1 | 4 | O | 1 | = | 1
| O | B | 0 | 6 | A | 0 | = | 0
| O | C | 0 | 5 | B | 0 | = | 0
| A | B | 1 | 1 | C | 0 | = | 0
| А | D | 0 | 7 | D | 0 | = | 0
| В | C | 0 | 2 | E | 0 | = | 0
| B | D | 1 | 5.5 | T | -1 | = | -1
| B | Е | 0 | 4
| C | B | 0 | 5
| D | Е | 0 | 1
| D | T | 1 | 6
| Е | T | 0 | 8
|  | TotaI Distance | 16.5

## Max Flow2
City Water Flow Maximisation
| From | To | Flow |  | Capacity | Nodes | NetFIow |  | Supply/Oemand
| R1 | A | 75 | <= | 75 | R1 | 140 | = | 140
| R1 | B | 65 | <= | 65 | R2 | 140 | = | 140
| R2 | A | 30 | <= | 40 | R3 | 115 | = | 115
| R2 | B | 50 | <= | 50 | A | 0 | = | 0
| R2 | C | 60 | <= | 60 | B | 0 | = | 0
| R3 | B | 45 | <= | 80 | C | 0 | = | 0
| R3 | C | 70 | <= | 70 | D | 0 | = | 0
| A | D | 60 | <= | 60 | E | 0 | = | 0
| A | E | 45 | <= | 45 | F | 0 | = | 0
| B | D | 60 | <= | 70 | T | -395 | = | -395
| B | E | 55 | <= | 55
| B | F | 45 | <= | 45
| C | E | 45 | <= | 70
| C | F | 85 | <= | 90
| D | T | 120 | <= | 120
| E | T | 145 | <= | 190
| F | T | 130 | <= | 130
|  | Max Flow | 395

## Max Flow3
Oil Flow Maximisation
| From | To | Flow |  | Capacity (Thousands of Barrels) | Nodes | NetFIow |  | Supply/Oemand
| Texas | New Orleans | 11 | <= | 11 | Texas | 28 | = | 28
| Texas | Charleston | 7 | <= | 7 | California | 24 | = | 24
| Texas | Seattle | 2 | <= | 2 | Alaska | 28 | = | 28
| Texas | St. Louis | 8 | <= | 8 | Middle East | 28 | = | 28
| California | New Orleans | 5 | <= | 5 | New Orleans | 0 | = | 0
| California | Charleston | 4 | <= | 4 | Charleston | 0 | = | 0
| California | Seattle | 8 | <= | 8 | Seattle | 0 | = | 0
| California | St. Louis | 7 | <= | 7 | St. Louis | 0 | = | 0
| Alaska | New Orleans | 7 | <= | 7 | Pittsburgh | -26 | = | -26
| Alaska | Charleston | 3 | <= | 3 | Atlanta | -33 | = | -33
| Alaska | Seattle | 12 | <= | 12 | Kansas City | -30 | = | -30
| Alaska | St. Louis | 6 | <= | 6 | San Francisco | -19 | = | -19
| Middle East | New Orleans | 1 | <= | 8
| Middle East | Charleston | 9 | <= | 9
| Middle East | Seattle | 3 | <= | 4 | Max Flow | 108 |  | -108
| Middle East | St. Louis | 15 | <= | 15
| New Orleans | Pittsburgh | 5 | <= | 5
| New Orleans | Atlanta | 9 | <= | 9
| New Orleans | Kansas City | 6 | <= | 6
| New Orleans | San Francisco | 4 | <= | 4
| Charleston | Pittsburgh | 8 | <= | 8
| Charleston | Atlanta | 7 | <= | 7
| Charleston | Kansas City | 8 | <= | 9
| Charleston | San Francisco | 0 | <= | 5
| Seattle | Pittsburgh | 4 | <= | 4
| Seattle | Atlanta | 6 | <= | 6
| Seattle | Kansas City | 7 | <= | 7
| Seattle | San Francisco | 8 | <= | 8
| St. Louis | Pittsburgh | 9 | <= | 12
| St. Louis | Atlanta | 11 | <= | 11
| St. Louis | Kansas City | 9 | <= | 9
| St. Louis | San Francisco | 7 | <= | 7

## Min Cost2
Makonsel Company Distribution
| From | To | Ship |  | Shipping Capacity | UnitCost in (100$) | Nodes | NetFIow |  | Supply/Demand
| Plant 1 | Warehouse 1 | 125 | <= | 125 | 425 | Plant 1 | 200 | = | 200
| Plant 1 | Warehouse 2 | 75 | <= | 150 | 560 | Plant 2 | 300 | = | 300
| Plant 2 | Warehouse 1 | 125 | <= | 175 | 510 | Warehouse 1 | 0 | = | 0
| Plant 2 | Warehouse 2 | 175 | <= | 200 | 600 | Warehouse 2 | 0 | = | 0
| Warehouse 1 | R01 | 100 | <= | 100 | 470 | R01 | -150 | = | -150
| Warehouse 1 | R02 | 50 | <= | 150 | 505 | R02 | -200 | = | -200
| Warehouse 1 | R03 | 100 | <= | 100 | 490 | R03 | -150 | = | -150
| Warehouse 2 | R01 | 50 | <= | 125 | 390
| Warehouse 2 | R02 | 150 | <= | 150 | 410
| Warehouse 2 | R03 | 50 | <= | 75 | 440
|  | Total Cost | 488125

## Min Cost3
Audiofile Company Shipements
per 1k speakers
| From | To | Ship | Vendor prices | Distance | Shipping Cost | Cost per mile | Nodes | NetFIow |  | Supply/Demand
| Vendor 1 | Warehouse 1 | 0 | 22500 | 1600 | 300 | 40 | Vendor 1 | 6 | = | 6
| Vendor 1 | Warehouse 2 | 6 | 22500 | 400 | 300 | 40 | Vendor 2 | 4 | = | 6
| Vendor 2 | Warehouse 1 | 4 | 22700 | 500 | 200 | 50 | Vendor 3 | 6 | = | 6
| Vendor 2 | Warehouse 2 | 0 | 22700 | 600 | 200 | 50 | Warehouse 1 | 0 | = | 0
| Vendor 3 | Warehouse 1 | 0 | 22300 | 2000 | 500 | 20 | Warehouse 2 | 0 | = | 0
| Vendor 3 | Warehouse 2 | 6 | 22300 | 1000 | 500 | 20 | Factory 1 | -10 | = | -10
| Warehouse 1 | Factory 1 | 4 | 0 | 0 | 200 | 0 | Factory 2 | -6 | = | -6
| Warehouse 1 | Factory 2 | 0 | 0 | 0 | 700 | 0
| Warehouse 2 | Factory 1 | 6 | 0 | 0 | 400 | 0
| Warehouse 2 | Factory 2 | 6 | 0 | 0 | 500 | 0
|  | Total Cost | 687400

## Min Cost4
Distribution Minimun Cost Flow Problem
| From | To | Ship |  | Capacity | UnitCost in (100$) | Nodes | NetFIow |  | Supply/Demand
| A | D | 40 | <= | 40 | 6 | A | 50 | = | 50
| A | C | 10 |  |  | 4 | B | 80 | = | 80
| B | A | 0 |  |  | 1 | C | 0 | = | 0
| B | C | 40 |  |  | 2 | D | -70 | = | -70
| B | E | 40 | <= | 40 | 5 | E | -60 | = | -60
| C | D | 30 |  |  | 3
| C | E | 20 |  |  | 5
|  | Total Cost | 750

## Case Study
Currency Market Forex
| From | To | Amount |  | Transaction Limits ($) | Transaction Cost (%) | Transaction Rate | Nodes | NetFIow |  | Supply/Demand
| Yen | Rupiah | 0 | <= | 5000000 | 0.5% | 50 | Yen | 9600000 | = | 9600000 | 1200000000 | yen
| Yen | Ringgit | 0 | <= | 5000000 | 0.5% | 0.04 | Rupiah | 1680000 | = | 1680000 | 10500000000 | rupiah
| Yen | U.S. dollar | 2000000 | <= | 2000000 | 0.4% | 0.008 | Ringgit | 5600000 | = | 5600000 | 28000000 | ringgit
| Yen | Canadian dollar | 2000000 | <= | 2000000 | 0.4% | 0.01 | Canadian Dollar | 0 | = | 0 | 2
| Yen | Euro | 2000000 | <= | 2000000 | 0.4% | 0.0064 | Euro | 0 | = | 0 | 3
| Yen | Pound | 2000000 | <= | 2000000 | 0.25% | 0.0048 | Pound | 0 | = | 0 | 4
| Yen | Peso | 1600000 | <= | 4000000 | 0.5% | 0.0768 | Peso | 0 | = | 0 | 5
| Rupiah | Yen | 0 | <= | 5000000 | 0.5% | 0.02 | U.S. Dollar | -16880000 | = | -16880000 | 1
| Rupiah | Ringgit | 0 | <= | 200000 | 0.7% | 0.0008
| Rupiah | U.S. dollar | 200000 | <= | 200000 | 0.5% | 0.00016
| Rupiah | Canadian dollar | 200000 | <= | 200000 | 0.3% | 0.0002
| Rupiah | Euro | 1000000 | <= | 1000000 | 0.3% | 0.000128
| Rupiah | Pound | 80000 | <= | 500000 | 0.75% | 9.6e-05
| Rupiah | Peso | 200000 | <= | 200000 | 0.75% | 0.001536
| Ringgit | Yen | 0 | <= | 3000000 | 0.5% | 25
| Ringgit | Rupiah | 0 | <= | 4500000 | 0.7% | 1250
| Ringgit | U.S. dollar | 1100000 | <= | 1500000 | 0.7% | 0.2
| Ringgit | Canadian dollar | 0 | <= | 1500000 | 0.7% | 0.25
| Ringgit | Euro | 2500000 | <= | 2500000 | 0.4% | 0.16
| Ringgit | Pound | 1000000 | <= | 1000000 | 0.45% | 0.12
| Ringgit | Peso | 1000000 | <= | 1000000 | 0.5% | 1.92
| Canadian Dollar | U.S. dollar | 2200000 |  | 0 | 0.05% | 0.8
| Euro | U.S. dollar | 5500000 |  | 0 | 0.1% | 1.25
| Pound | U.S. dollar | 3080000 |  | 0 | 0.1% | 1.6667
| Peso | U.S. dollar | 2800000 |  | 0 | 0.1% | 0.10417
|  | Total Cost | 83380